## Product Backlog
Story ID | Epic | User Story Statement | Story Points | Acceptance Criteria | Status
US-101 | Epic 1: Ingestion Engine | As a User, I want to upload PDF, DOCX, TXT, and CSV documents so that system can index enterprise knowledge. | 5 | Supports PyMuPDF, python-docx, TXT, pandas extraction with error handling. | DONE
US-102 | Epic 1: Ingestion Engine | As a User, I want text split into chunks with configurable size and overlap so that retrieval yields precise passages. | 3 | LangChain RecursiveCharacterTextSplitter configured with sliders (200-1500 chars). | DONE
US-103 | Epic 1: Ingestion Engine | As a System, I want text chunks converted to vector embeddings and stored persistently in ChromaDB & SQLite. | 5 | all-MiniLM-L6-v2 dense vectors indexed in ChromaDB; metadata stored in SQLite. | DONE
US-201 | Epic 2: Multi-Agent Pipeline | As a System, I want a Query Understanding Agent to classify queries as Factual, Procedural, Comparative, or Ambiguous. | 5 | Query classified correctly and routed to resolution path (factual_direct, procedural_workflow, etc.). | DONE
US-202 | Epic 2: Multi-Agent Pipeline | As a System, I want a Retrieval Agent to rank chunks using hybrid scoring and filter out low-confidence results. | 5 | Hybrid score (70% Cosine + 30% Keyword Density) applied; chunks <0.35 threshold removed. | DONE
US-203 | Epic 2: Multi-Agent Pipeline | As a System, I want a Response Generation Agent to synthesize path-tailored answers with source citations & confidence meters. | 5 | Answers formatted as steps/tables with exact file citations and High/Medium/Low confidence badge. | DONE
US-204 | Epic 2: Multi-Agent Pipeline | As a System, I want a Multi-Agent Orchestrator to coordinate agent execution sequentially and log latency telemetry. | 3 | Sequential execution logged with per-agent latency in milliseconds (latency_ms). | DONE
US-301 | Epic 3: Voice UI & Workspace | As a User, I want to dictate queries via microphone and hear answers read aloud using Web Speech API. | 5 | Speech-to-Text (SpeechRecognition) and Text-to-Speech (SpeechSynthesis) integrated. | DONE
US-302 | Epic 3: Voice UI & Workspace | As a User, I want a Knowledge Base Browser with a View Chunks button to inspect document chunk segments. | 3 | Table renders 18 documents with cyan View Chunks modal button. | DONE
US-401 | Epic 4: Accuracy Benchmark | As a User, I want an automated retrieval accuracy benchmark evaluating Top-1, Top-3, and Top-5 recall across domains. | 5 | Automated 10-query benchmark suite verifies 100% accuracy score. | DONE
US-501 | Epic 5: Re-Ranking & Optimization | As a System, I want Cross-Encoder Re-Ranking model integration to optimize top 10 passage selection. | 8 | Cross-Encoder model reranks initial vector recall set. | PLANNED
US-502 | Epic 5: Re-Ranking & Optimization | As a System, I want BM25 sparse keyword indexing combined with ChromaDB dense vectors for hybrid search. | 5 | BM25 index integrated with vector similarity search. | PLANNED

## Sprint Planning
Sprint | Goal | Duration | Planned Points | Completed Points | Status
Sprint 1 (Milestone 1) | Knowledge Base Ingestion Engine & Vector Store Setup | 2 Weeks | 21 | 21 | CLOSED - 100% SUCCESS
Sprint 2 (Milestone 2) | Multi-Agent Query Resolution Pipeline & Path Synthesis | 2 Weeks | 23 | 23 | CLOSED - 100% SUCCESS
Sprint 3 (Milestone 3) | Advanced Search & Re-Ranking Optimization | 2 Weeks | 13 | 0 | PLANNED

## Sprint Retrospective
Sprint | Category | Details
Sprint 1 | What Went Well | Integrated PyMuPDF, python-docx, pandas, and TXT extractors cleanly; LangChain text splitting preserved sentence bounds.
Sprint 1 | What Could Be Improved | Text extraction from legacy non-UTF-8 files required multi-encoding fallback reader.
Sprint 1 | Action Items | Added multi-encoding reader in extractor.py and 1-Click Seed Sample Knowledge Base button.
Sprint 2 | What Went Well | Query Understanding Agent classifies queries cleanly; hybrid scoring filtered out low-confidence noise chunks (<0.35); achieved 100% benchmark accuracy.
Sprint 2 | What Could Be Improved | Comparative queries required dedicated comparative matrix templates.
Sprint 2 | Action Items | Added comparative matrix resolution path synthesis and per-agent latency telemetry.

## Project Charter
Framework Section | Details
Vision Statement | Build an enterprise-grade multi-agent RAG retrieval platform with 100% verified accuracy across multi-format datasets.
Definition of Ready (DoR) | User story written, acceptance criteria testable, Fibonacci story points estimated, endpoints and data models identified.
Definition of Done (DoD) | Backend code unit tested, frontend builds cleanly with 0 errors (npm run build), evaluation accuracy verified, Git committed.
Team Roles | Product Owner (Mentorship Team), Scrum Master (Agile Lead), AI Systems Engineer, Frontend Developer.

## Burndown & Velocity
Sprint | Day | Remaining Points | Milestone Activity
Sprint 1 | Day 1 | 21 | Sprint Backlog Refinement & Architecture Design
Sprint 1 | Day 3 | 16 | PyMuPDF, docx, pandas, and TXT extractors completed (US-101)
Sprint 1 | Day 5 | 13 | LangChain text chunking & sliders integrated (US-102)
Sprint 1 | Day 7 | 8 | SentenceTransformers & ChromaDB persistent store (US-103)
Sprint 1 | Day 9 | 5 | Document Browser & Chunk Viewer Modal completed (US-302)
Sprint 1 | Day 10 | 0 | Retrieval Accuracy Benchmark Suite completed (US-401)
Sprint 2 | Day 1 | 23 | Sprint 2 Backlog Refinement & Multi-Agent Design
Sprint 2 | Day 3 | 18 | Query Understanding Agent classification & routing (US-201)
Sprint 2 | Day 5 | 13 | Retrieval Agent hybrid ranking & 0.35 filtering (US-202)
Sprint 2 | Day 7 | 8 | Response Gen Agent path templates & confidence meter (US-203)
Sprint 2 | Day 9 | 5 | Multi-Agent Orchestrator & latency telemetry (US-204)
Sprint 2 | Day 10 | 0 | Web Speech API Voice UI (STT & TTS) completed (US-301)