## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Implement PyMuPDF document extractor for PDF document ingestion | Must Have | None | Backend Lead | Completed
Sprint 1 | Sprint 1 | US-002 | Implement python-docx extractor for DOCX document ingestion | Must Have | US-001 | Backend Lead | Completed
Sprint 1 | Sprint 1 | US-003 | Implement CSV & TXT data preprocessing pipeline | Must Have | None | Data Engineer | Completed
Sprint 1 | Sprint 1 | US-004 | Build RecursiveCharacterTextSplitter chunking engine (500 char, 50 overlap) | Must Have | US-001 | AI Specialist | Completed
Sprint 1 | Sprint 1 | US-005 | Integrate SentenceTransformers all-MiniLM-L6-v2 vector embeddings (384-dim) | Must Have | US-004 | AI Specialist | Completed
Sprint 1 | Sprint 1 | US-006 | Setup ChromaDB local persistent vector store HNSW collection | Must Have | US-005 | Database Engineer | Completed
Sprint 1 | Sprint 1 | US-007 | Setup SQLite metadata DB for tracking document records & chunk maps | Must Have | None | Database Engineer | Completed
Sprint 1 | Sprint 1 | US-008 | Create React Web UI for Document Upload & Ingestion Status | Must Have | Frontend Lead | Frontend Lead | Completed
Sprint 1 | Sprint 1 | US-009 | Integrate Web Speech API for voice search (STT) and response reading (TTS) | Should Have | US-008 | Frontend Lead | Completed
Sprint 1 | Sprint 1 | US-010 | Build Retrieval Evaluation & Accuracy Benchmark Suite | Must Have | US-006 | QA Lead | Completed
Sprint 2 | Sprint 2 | US-011 | Build M2.1 Query Understanding Agent for taxonomy & ambiguity detection | Must Have | None | AI Specialist | Completed
Sprint 2 | Sprint 2 | US-012 | Build M2.2 Hybrid Retrieval Agent with Cosine + Keyword density scoring | Must Have | US-006 | AI Specialist | Completed
Sprint 2 | Sprint 2 | US-013 | Build M2.3 Response Generation Agent with grounded synthesis & confidence badges | Must Have | US-012 | AI Specialist | Completed
Sprint 2 | Sprint 2 | US-014 | Build M2.4 Multi-Agent Orchestrator for sequential pipeline & per-step try-except | Must Have | US-011 | Backend Lead | Completed
Sprint 2 | Sprint 2 | US-015 | Build Multi-Agent Query UI workspace & Agent Architecture visualizer tab | Must Have | US-014 | Frontend Lead | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | TS-01 | Setup PyMuPDF & pdfplumber PDF extraction module | 2026-08-25 | 2026-08-26 | Backend Lead | Development | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TS-02 | Setup python-docx paragraph and table parser | 2026-08-26 | 2026-08-27 | Backend Lead | Development | Completed | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TS-03 | Build CSV pandas & TXT text cleaner module | 2026-08-27 | 2026-08-28 | Data Engineer | Development | Completed | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TS-04 | Implement RecursiveCharacterTextSplitter engine | 2026-08-28 | 2026-08-29 | AI Specialist | Development | Completed | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TS-05 | Integrate SentenceTransformers all-MiniLM-L6-v2 embeddings | 2026-08-29 | 2026-08-30 | AI Specialist | Development | Completed | 12 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TS-06 | Setup ChromaDB vector store collection & HNSW index | 2026-08-30 | 2026-08-31 | Database Engineer | Database | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TS-07 | Build SQLite metadata DB schema & document CRUD API | 2026-08-31 | 2026-09-01 | Database Engineer | Database | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TS-08 | Create React Ingestion & Knowledge Browser UI components | 2026-09-01 | 2026-09-02 | Frontend Lead | UI Design | Completed | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 0
US-009 | TS-09 | Integrate Web Speech API STT voice search & TTS reader | 2026-09-02 | 2026-09-03 | Frontend Lead | UI Design | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 3 | 0 | 0 | 0
US-010 | TS-10 | Build Benchmark Evaluation framework & run accuracy test | 2026-09-03 | 2026-09-04 | QA Lead | Testing | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0
SPRINT 2 BACKLOG
US-011 | TS-11 | Build M2.1 Query Understanding Agent taxonomy rules | 2026-09-04 | 2026-09-05 | AI Specialist | Development | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TS-12 | Build M2.2 Hybrid Retrieval Agent (70% Vector + 30% Keyword) | 2026-09-05 | 2026-09-06 | AI Specialist | Development | Completed | 14 | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | TS-13 | Build M2.3 Response Generator with citations & confidence badges | 2026-09-06 | 2026-09-07 | AI Specialist | Development | Completed | 12 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | TS-14 | Build M2.4 Sequential Multi-Agent Orchestrator & error wrappers | 2026-09-07 | 2026-09-08 | Backend Lead | Development | Completed | 14 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | TS-15 | Build React Query Workspace & Agent Architecture Visualizer UI | 2026-09-08 | 2026-09-08 | Frontend Lead | UI Design | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | PyMuPDF installation dependency warning on Windows OS | Added PyMuPDF C++ runtime binaries & updated requirements.txt
Sprint 1 | Day 3 | Large CSV tabular files taking high memory during chunking | Optimized pandas chunking algorithm with batch size 50
Sprint 1 | Day 5 | SentenceTransformers model downloading on every server start | Cached model locally in backend/models directory for instant load
Sprint 1 | Day 7 | Web Speech API microphone permission denied in Chrome browser | Configured HTTPS localhost flag and added user permission fallback UI prompt
Sprint 1 | Day 10 | Benchmark score calculation latency on multi-query execution | Parallelized vector query evaluation across test suite queries
Sprint 2 | Day 1 | Ambiguous query classification false positives on short technical terms | Fine-tuned intent regex rules & word count threshold limits
Sprint 2 | Day 3 | Hybrid retrieval keyword weight overpowering vector distance score | Rebalanced weighting to 70% Cosine Vector + 30% Keyword Density
Sprint 2 | Day 5 | LLM response generation delay when API key is missing | Implemented local grounded extractive fallback generator with source attribution
Sprint 2 | Day 7 | Orchestrator failing completely if memory agent throws exception | Wrapped each agent execution step in individual try-except blocks
Sprint 2 | Day 10 | UI latency display missing per-agent timing breakdown | Added latency_ms telemetry array to API response payload

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-25 | 2026-09-04 | Sumanth K | Writing automated unit test cases alongside feature code | Committing large binary files directly to repository | Daily standup meeting syncs and prompt issue resolution | Configured .gitignore for venv, node_modules, and binary databases
2 | Sprint 1 | 2026-08-25 | 2026-09-04 | AI Lead | Standardizing embedding dimension checks (384-dim) | Hardcoding file paths across scripts | Benchmarking accuracy after every dataset ingestion | Created backend/config.py central configuration module
3 | Sprint 1 | 2026-08-25 | 2026-09-04 | QA Lead | Creating automated evaluation scripts for Top-1/Top-3/Top-5 metrics | Manual UI testing of vector search | Verifying multi-format file extractions | Built backend/eval/evaluate.py benchmark suite
4 | Sprint 2 | 2026-09-04 | 2026-09-08 | Sumanth K | Adding comprehensive try-except wrappers for agent pipeline steps | Exposing bracketed milestone tags in user interface | Strict multi-agent sequential orchestration | Cleaned UI headers and added robust error handling in orchestrator
5 | Sprint 2 | 2026-09-04 | 2026-09-08 | AI Lead | Structured output schemas (query_type, classification_confidence) | Relying solely on external LLM without fallback | Hybrid relevance ranking (70% Vector + 30% Keyword) | Implemented grounded fallback response generator
6 | Sprint 2 | 2026-09-04 | 2026-09-08 | Frontend Lead | Dynamic confidence level badge rendering (High/Med/Low) | Fixed pixel layout math for mobile viewports | Voice STT/TTS search integration | Enhanced QueryWorkspace & Architecture View components
7 | Sprint 2 | 2026-09-04 | 2026-09-08 | QA Lead | Defect tracking with severity classification & action taken verification | Skipping error recovery test scenarios | 100% benchmark evaluation threshold enforcement | Verified 100.0% retrieval accuracy across IT Cloud & Healthcare domains