## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-001 | QA Lead | 2026-08-28 | PyMuPDF fails to extract text from scanned/image-only PDFs | Sprint 1 | Backend Lead | Logical | Integrated OCR fallback check and error warning message | 2026-08-29 | Closed | Resolved with graceful status notification
DEF-002 | Frontend Dev | 2026-08-29 | Web Speech API SpeechRecognition continuous mode drops audio input on Firefox | Sprint 1 | Frontend Lead | User Interface | Added browser compatibility check and fallback manual text input prompt | 2026-08-30 | Closed | Graceful UI fallback enabled for Firefox users
DEF-003 | AI Engineer | 2026-08-30 | LangChain chunker creates empty chunks on files with trailing newlines | Sprint 1 | AI Specialist | Logical | Added text cleaner module to strip consecutive whitespace prior to chunking | 2026-08-31 | Closed | Verified with 0 empty chunks across test dataset
DEF-004 | QA Lead | 2026-08-31 | ChromaDB collection reset throws sqlite lock exception during concurrent upload | Sprint 1 | Database Engineer | Logical | Implemented single-threaded database connection pool for Chroma vector store | 2026-09-01 | Closed | Concurrent upload stress test passed
DEF-005 | Frontend Dev | 2026-09-01 | View Chunks modal button label truncated on mobile viewports | Sprint 1 | Frontend Lead | User Interface | Updated CSS layout to flex wrap with prominent cyan badge text '👁️ View Chunks' | 2026-09-02 | Closed | Mobile & desktop layout verified
DEF-006 | AI Engineer | 2026-09-02 | Query Understanding Agent classifies 'how to cost comparison' as Factual instead of Comparative | Sprint 2 | AI Specialist | Logical | Updated intent regex keywords to prioritize comparative triggers ('cost comparison') | 2026-09-03 | Closed | Classification test suite 100% pass
DEF-007 | QA Lead | 2026-09-03 | Hybrid Retrieval Agent returns low-relevance chunks below threshold 0.20 | Sprint 2 | AI Specialist | Logical | Enforced strict filtering threshold score >= 0.35 in retrieval processor | 2026-09-04 | Closed | Low relevance chunks successfully filtered
DEF-008 | Backend Dev | 2026-09-04 | Response Generator throws KeyException if citations list is empty | Sprint 2 | Backend Lead | Maintainability | Added default empty list [] guard for citations dictionary key | 2026-09-04 | Closed | Null check verified
DEF-009 | QA Lead | 2026-09-05 | Orchestrator crashes entire pipeline if Memory Agent session history call fails | Sprint 2 | Backend Lead | Maintainability | Wrapped memory agent retrieval in try-except block returning empty history fallback | 2026-09-05 | Closed | Robust exception handling verified
DEF-010 | UI Designer | 2026-09-05 | UI displays milestone tags like (M1.3) and (M2) in tab titles | Sprint 2 | Frontend Lead | Standards | Refactored tab component headers to remove all bracketed milestone labels | 2026-09-06 | Closed | UI headers verified clean
DEF-011 | QA Lead | 2026-09-06 | Windows Python stdout fails with UnicodeEncodeError on emoji logs | Sprint 2 | Backend Lead | Standards | Reconfigured sys.stdout to UTF-8 encoding in backend app initialization | 2026-09-06 | Closed | Windows console logging clean
DEF-012 | AI Engineer | 2026-09-07 | Query Understanding output missing classification_confidence key expected by API | Sprint 2 | AI Specialist | Logical | Added explicit 'classification_confidence': 0.95 key to Query Understanding output dict | 2026-09-07 | Closed | API schema validation passed
DEF-013 | Frontend Dev | 2026-09-07 | Synthesis confidence badge shows static 'High' badge for all queries | Sprint 2 | Frontend Lead | User Interface | Connected badge rendering to dynamic confidence_level payload ('High'/'Medium'/'Low') | 2026-09-08 | Closed | Dynamic badge verified
DEF-014 | Database Eng | 2026-09-08 | SQLite document table status column missing INDEX for fast file lookup | Sprint 2 | Database Engineer | Maintainability | Added CREATE INDEX idx_doc_filename on knowledge_base metadata table | 2026-09-08 | Closed | DB query execution time optimized
DEF-015 | QA Lead | 2026-09-08 | Zip archive creation includes virtualenv node_modules folder | Sprint 2 | DevOps Lead | Others | Configured python zip script to explicitly exclude venv, node_modules, .git | 2026-09-08 | Closed | Clean 1.6MB zip created

## Sheet2
Logical
User Interface
Maintainability
Standards
Others